## Gantt Chart
Task | Start Date | End Date | Duration (days) | Owner | Dependencies | Status
Initiation | 2025-10-01 | 2025-10-31 | 30 | PMO |  | Planned
Data Platform Setup | 2025-11-01 | 2025-12-31 | 61 | Cloud Lead | Initiation | Planned
Model Development | 2026-01-01 | 2026-03-31 | 90 | AI Lead | Data Platform Setup | Planned
Integration & Testing | 2026-04-01 | 2026-05-31 | 61 | DevOps | Model Development | Planned
Pilot & Rollout | 2026-06-01 | 2026-06-30 | 30 | Ops | Integration & Testing | Planned

## Resource Allocation
Function | FTE | Roles
AI/ML | 4 | Data Scientist, MLOps
Cloud | 3 | Architect, Infra Engg
Scrum | 1 | Scrum Master
PMO | 2 | Program Lead, Risk Manager
Client | 2 | DoT Rep, IT Security