## Risk_Register
ID | Risk | Likelihood | Impact | Owner | Mitigation | Status
1 | Data Privacy Breach | 5 | 5 | CISO | Encrypt PII, access controls | Open
2 | Model Bias | 4 | 4 | Data Science Lead | Bias tests, representative data | Open
3 | Integration Delay | 3 | 4 | Infra Lead | Staggered APIs, mocks | Open
4 | Change Resistance | 3 | 3 | Change Manager | Stakeholder engagement | Open
5 | Model Drift | 3 | 4 | MLOps Lead | Monitoring & retrain schedule | Open