## Project_Plan
Task | Start | End | Owner | Status
Discovery & Data Collection | 2025-10-06 | 2025-10-20 | PM | Completed
Model Development | 2025-10-21 | 2025-11-20 | DS Lead | In Progress
Integration & Testing | 2025-11-21 | 2025-12-15 | Infra | Planned
UAT & Rollout | 2025-12-16 | 2026-01-04 | PM | Planned